## Gantt Chart
GANTT CHART
PROJECT TITLE |  | POS - Power House Phitness (PHP) |  |  |  |  | ORGANIZATION NAME | [6 empty] | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE | [6 empty] | 2022-10-12
GROUP LEADER |  | Charles Olinsky
GROUP MEMBERS |  | Erica Dubie, Beesanne Kurzum, Olamide Kumapayi, Christina Rodriguez
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/8/2022 |  |  |  |  | W2 9/15/2022 |  |  |  |  | W3 9/22/2022 |  |  |  |  | W4 9/29/2022 |  |  |  |  | W5 10/6/2022 |  |  |  |  | W6 10/10/2022 |  |  |  |  | W7 10/17/2022 |  |  |  |  | W8 10/27/2022 |  |  |  |  | W9 11/3/2022 |  |  |  |  | W10 11/10/2021 |  |  |  |  | W11 11/17/2021 |  |  |  |  | W12 11/24/2021 |  |  |  |  | W13 12/1/2021 |  |  |  |  | W14 12/8/2021
1 | Proct Conception and Initiation | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100%
1.1.1 | Setting up Discord | All | 2022-09-05 | 2022-09-05 | 0 | 100%
1.2 | Setting up XAMPP | All | 2022-09-06 | 2022-09-08 | 2 | 100%
1.3 | Assigning Group Leader | All | 2022-09-06 | 2022-09-06 | 0 | 100%
1.4 | Deciding on a Concept | All | 2022-09-05 | 2022-09-05 | 0 | 100%
1.5 | Create Directory Structure | Charlie | 2022-09-20 | 2022-09-20 | 0 | 100%
1.6 | Clarify Concept - Fitness Center | All | 2022-09-26 | 2022-09-26 | 0 | 100%
1.7 | Decide on Project Name | All | 2022-09-26 | 2022-09-26 | 0 | 100%
2 | Planning
2.1 | Users - 3 classes | Christina |  |  | 0 | 0%
2.2 | Financial Reports - Z Reports - CashFlow | Christina |  |  | 0 | 0%
2.3 | Inventory - Details - Vendor - TTL | Beesanne |  |  | 0 | 0%
2.3.1 | Services | Erica, Beesanne |  |  | 0 | 0%
2.4 | Shopping Cart - Payment | Olamide |  |  | 0 | 0%
2.5 | Reciepts | Olamide |  |  | 0 | 0%
2.6 | Security | Charlie |  |  | 0 | 0%
2.7 | Sessions Class | Charlie |  |  | 0 | 0%
2.8 | Data Management | Beesanne |  |  | 0 | 0%
2.9 | UI | Erica |  |  | 0 | 0%
2.1 | Email Notifications | Charlie |  |  | 0 | 0%
2.11
3 | Coding and Assembly
Charlie
Sessions Class
Intialize the Sessions class | bar: W6 10/10/2022 W to W6 10/10/2022 F
Meet with Denizard to discuss implementation | bar: W7 10/17/2022 W to W8 10/27/2022 W
Begin using HTTP Only Cookies in sessions | bar: W7 10/17/2022 W to W8 10/27/2022 M
Integrate Sessions into User Class | bar: W7 10/17/2022 W to W8 10/27/2022 W
Integrate Sessions into Shopping Cart Class | bar: W8 10/27/2022 W to W9 11/3/2022 W
Security
Begin Encrypting Data | bar: W6 10/10/2022 W to W6 10/10/2022 F
Create password hashing function | bar: W7 10/17/2022 W to W8 10/27/2022 M
Change DB Connector to PDO | bar: W7 10/17/2022 W to W7 10/17/2022 F
Integrate Security and User Classes | bar: W7 10/17/2022 W to W8 10/27/2022 F
Christina
Create Test Table PHPmyAdminj | bar: W6 10/10/2022 W to W7 10/17/2022 M
Implement SQL Queries in User Class Functions | bar: W6 10/10/2022 W to W7 10/17/2022 M
Test Creation of all 5 users | bar: W6 10/10/2022 W to W7 10/17/2022 M
error handeling
connect to login
roles class with access levels
Store Order History
Financial
php code for calculations
different report ypes
report on type of serve
test tables for reports
Erica
link landing page to login | bar: W6 10/10/2022 T to W7 10/17/2022 M
add profie link | bar: W6 10/10/2022 T to W7 10/17/2022 M
finalize navbar | bar: W6 10/10/2022 T to W7 10/17/2022 M
add shopping cart | bar: W6 10/10/2022 T to W7 10/17/2022 M
all links functioning | bar: W6 10/10/2022 T to W7 10/17/2022 M
make diagrams for UI Plan
Beesanne
Inventory
Rental Checkout Customer Page to Display DB Info | bar: W6 10/10/2022 M to W7 10/17/2022 M
Rental Check-in Employee Portal
Admin Inventory Page
Product Tables with Data | bar: W6 10/10/2022 R to W7 10/17/2022 M
Upload to XAMMP | bar: W6 10/10/2022 R to W7 10/17/2022 M
Add Data for Products | bar: W6 10/10/2022 R to W7 10/17/2022 M
Work with Olamide to get Add to cart button functioning on Rental page | bar: W7 10/17/2022 W to W8 10/27/2022 M
Meet with Christina to Finalize Users Tables and upload to XAMMP | bar: W7 10/17/2022 W to W8 10/27/2022 M
Database
Create Products Table | bar: W6 10/10/2022 T to W7 10/17/2022 M
Add Data to Unchanging Tables
Olamide
working shopping cart class | bar: W5 10/6/2022 M to W7 10/17/2022 M
wokring DB | bar: W5 10/6/2022 M to W7 10/17/2022 M
Finish shopping cart form page | bar: W7 10/17/2022 W to W8 10/27/2022 M
work with Beesane to get Add to cart button functioning on retail page | bar: W7 10/17/2022 W to W9 11/3/2022 M
4 | Meetings
4.1 | Webex Group Week 1 | All | N/A | N/A | #VALUE! | 100%
4.2 | Webex Group Week 2 | All | N/A | N/A | 0 | 100%
4.2.1 | Webex Group Week 3 | All | 2022-09-19 | 2022-09-19 | 0 | 100%
9/ | Webex Denizard: UI / General | Erica, All Optional | 2022-09-25 | 2022-09-25 | 0 | 100%
4.3.2 | Webex Group Week 4 | All | 2022-09-26 | 2022-09-26 | 0 | 100%
4.3.3 | Webex Group Week 5 | All | 2022-10-03 | 2022-10-03 | 0 | 100%
| Webex Group Week 6 | All | 2022-10-10 | 2022-10-10 | 0 | 100%
4.3.3 | In-Person Group Week 6 | All | 2022-10-10 | 2022-10-10 | 0 | 100%